## Sheet1
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Indicator | Contingency Plan | Responsible | Status | Last modifed date
1 | Organization | Key team member leaves the project unexpectedly | 1 | 10 | 10 | Develop attractive compensation packages, offer professional development opportunities, and foster a positive work culture | Often absence; depressed team atmosphere; dedicated tasks are not done | Split required work on the other team members; Documentation of (completed) tasks \ work (DevOps) | Product Owner / Scrum Master | Open | 2023-04-13
2 | Project | Development-Equipment failure | 1 | 3 | 3 | Conduct regular maintenance and inspection of equipment to identify and fix any issues before they result in equipment failure. | Weird behavior; over heating | Develop a plan for quickly repairing or replacing failed equipment to minimize production downtime; Backup equipment | Team | Open | 2023-04-13
3 | Legal | License problems | 4 | 10 | 40 | Check recent product updates for changes (Photon, Unity) | Change-/Update Logs | Respond promptly to license regulatory inquiries | Team | Open | 2023-04-13
4 | Technical | Photon Hosting Service is temporarily unavailable | 3 | 5 | 15 | No influence | Photon company is not providing the hosting service for a certain time | Provide Hosting-Error display into our game; shows if the service / game is available | Photon | Open | 2023-04-13
5 | Technical | Photon Hosting Service is permanently offline | 1 | 10 | 10 | No influence | Photon company is not providing the hosting service; | Switch to another hosting provider | Photon | Open | 2023-04-13